## Sheet1
Phase | Milestone | End date | Status | Remarks
1 | Literature survey report | 2024-02-15 | DOING
1 | Experiment design | 2024-01-29 | DONE
1 | Documentation of observations | 2024-02-15 | DOING | 29-Jan: Communication problem in the command-response synchrony with the motor. Implementing a buffer on the Raspberry Pi -- synchrony problem exists.
2 | Algorithm design with scoring documented | 2024-03-29 | TODO | 1/29: Examiner has advised to start design as soon as feasible. Considering using IRL model as described in https://arxiv.org/pdf/1806.06877.pdf. 1/29: Using Gaussian modelling . To model interdependence between KTIs and then to define deviations from ideal state w.r.t. divergences in interdependence.
2 | Algorithm design with explainability documented | 2024-03-29 | TODO
3 | Documentation of results and conclusion | 2024-04-15 | TODO
3 | Thesis write up | 2024-04-30 | TODO
4 | Publication | 2024-05-31 | TODO